T21RS DS Models Assistant: LLM Testing Plan

## Summary & Objectives

Test the AI Research Assistant (LLM literature search grounded to a 1,200+ PubMed bibliography, default model only) of the T21RS DS Models Assistant across 12 testers from 6 institutions over 10 working days. This covers both the standard literature-search mode and the Deep Dive mode (verbatim Results/Methods/Figure-Legend extraction from PMC Open Access full text for up to 5 focus PMIDs).

Effort: ~30 minutes/person/day. All query volumes and the timeline are scaled to fit this. Other kinds of spreading effort are also fine, but we will keep the deadline constant.

Communication: We will communicate using a tool very similar to Slack and other chat-based collaboration tools – Zulip. We will use our dedicated Zulip portal (https://t21rsas.zulipchat.com/) for troubleshooting and progress updates.

Primary deliverable: a quantified accuracy + citation-validity assessment, a Deep Dive verbatim-fidelity assessment, and a prioritized bug list with beta-readiness recommendation.

Scope boundary: Only the AI Research Assistant feature (standard + Deep Dive modes). The model database, sample-size calculator, ARRIVE checklist, and model comparison are out of scope (tested only incidentally when they surface in an LLM answer).

Success criteria: (a) a scored query set exists, (b) rubric metrics are computed, (c) verification is completed on the tiered subset, (d) a prioritized bug list is filed as GitHub issues.

Testing begins: Friday, October 2nd, 2026. Deadline for Testing: Thursday, October 15th, 2026

## Roles & Team Allocation (12 researchers across 6 institutions)

Team composition:

University of Dayton (UD): Aaron Sathyanesan, Sanjay Madala, Emily Grace Sering

Indiana University (IU): Randall Roper, Linnea Johnson, Abi Duffin

UK Dementia Research Institute (UKDRI): Frances Wiseman

University of Queensland (UQ): Michelle Maugham-Macan, Sagar Regmi

Paris Brain Institute - ICM: Daniella B. Victorino

Sapienza University of Rome: Antonella Tramutola, Sara Pagnotta

| Role | Count | Who | Responsibility |
| --- | --- | --- | --- |
| Test Lead / Coordinator | 1 | Aaron Sathyanesan (UD) | Rubric design, scoring sheet, schedule, async check-ins, final consolidation |
| Developer | 1 | Sanjay Madala (UD) | Reproduces bugs, files/triages GitHub issues, tracks tool version/config |
| Domain Scorers | 7–8 | All institutions | Run assigned queries on default model, score rubric, citation-verify |
| Independent Verifiers | 2 | Linnea Johnson (IU) and Sanjay Madala (UD) | Independent PubMed re-synthesis for the 8 high-rigor queries + Deep Dive verbatim checks |

## Individual Responsibilities

| Name | Institution | Role(s) | Responsibilities / Assignments |
| --- | --- | --- | --- |
| Aaron Sathyanesan | UD | Test Lead / Coordinator | Rubric design, scoring sheet, schedule, daily async check-ins, final consolidation; outreach to all teams via Zulip |
| Sanjay Madala | UD | Developer + Independent Verifier (UD) | Reproduces bugs, files/triages GitHub issues, tracks tool version/config; Tier-1 re-synthesis and Deep Dive verbatim checks (UD half) |
| Emily Grace Sering | UD | Domain Scorer – MS | Queries 1–4 (model selection); calibration C1/C2; 2 wild-track questions; Tier-2 citation checks on own queries |
| Randall Roper | IU | Domain Scorer – AR | Queries 18–19 (ARRIVE reporting); calibration C1/C2; 2 wild-track questions; Tier-2 citation checks on own queries |
| Linnea Johnson | IU | Independent Verifier (IU) | Tier-1 independent PubMed re-synthesis and blinded comparison scoring; Deep Dive verbatim checks (IU half); must not score queries they verify |
| Abi Duffin | IU | Domain Scorer – GD | Queries 8–11 (Hsa21 gene dosage); calibration C1/C2; 2 wild-track questions; Tier-2 citation checks on own queries |
| Frances Wiseman | UKDRI | Domain Scorer – BP | Queries 5–7 (behavioral phenotypes); calibration C1/C2; 2 wild-track questions; Tier-2 citation checks on own queries |
| Michelle Maugham-Macan | UQ | Scorer – no fixed domain (backup) | Calibration C1/C2; 2 wild-track questions; absorbs queries if a scorer drops out |
| Sagar Regmi | UQ | Domain Scorer – PI | Queries 12–14 (pharmacological interventions); calibration C1/C2; 2 wild-track questions; Tier-2 citation checks on own queries |
| Daniella B. Victorino | ICM | Domain Scorer – AH | Queries 20–24 (anti-hallucination probes); calibration C1/C2; 2 wild-track questions; Tier-2 citation checks on own queries |
| Antonella Tramutola | Sapienza | Scorer – no fixed domain (backup) | Calibration C1/C2; 2 wild-track questions; absorbs queries if a scorer drops out |
| Sara Pagnotta | Sapienza | Domain Scorer – ED | Queries 15–17 (experimental design); calibration C1/C2; 2 wild-track questions; Tier-2 citation checks on own queries |

Scorers are assigned domains to avoid overlap; each query has exactly one scorer.

To keep baseline assessment steady, independent verifiers must not have authored or scored the query they verify. Cross-institution pairing will work in this way – for example: an Indiana Univ. verifier checks UD-scored queries; a Univ. of Queensland verifier checks ICM-scored queries; etc.

Aaron will reach out to each team to check in on progress via Zulip.

## Evaluation Framework

### Test query set – two tracks

Track A: Structured bank (~25 queries) – balanced across DS preclinical domains:

Model selection (which DS rodent model is appropriate for a given phenotype/question)

Behavioral phenotypes (learning/memory, motor, anxiety, seizure)

Hsa21 gene dosage & orthologs (e.g., Dyrk1a, App, Runx1, trisomic region contributions)

Pharmacological / cognitive interventions (memantine, EGCG, fluoxetine, etc.)

Experimental design (controls, sex as biological variable, age/stage)

ARRIVE-relevant reporting (what must be reported for a DS study)

Anti-hallucination probes (~5): a fabricated model name, a non-existent PMID, a real gene with a false claim, and a recent paper outside the bibliography window – to measure fabrication tendency and bibliography-coverage limits.

Query types within each domain: factual recall, synthesis/comparison, recommendation, and citation-heavy.

Track B: On-ground validation track (2 real questions/person) – each researcher submits 2 genuine current questions from their own work. Scored with the same rubric; supplemental evidence for “in-the-wild” use; will not be used for cross-query statistics.

Track C: Deep Dive (~8 queries) – tests the Deep Dive mode:

Suggestion-trigger logic (DD-1 to DD-3, Deep Dive OFF): does the lightbulb 💡 suggestion appear only when the user asks about 1-5 specific open access (OA) papers (and not for general questions or 6+ papers)?

Verbatim extraction (DD-4 to DD-6, Deep Dive ON, OA paper): does the model quote Results/Methods/Figure Legends from the actual PMC full text, with correct source labels and all numerical values extracted?

Non-OA refusal + "not stated" disciplined behavior (DD-7 to DD-8, Deep Dive ON): does it refuse section-level detail for non-OA papers and say "Not stated in the available text" for absent values rather than fabricating?

Optional edge cases (DD-9 to DD-10): named-only paper (no numeric PMID – focus detection may fail), and >5 PMIDs (only first 5 get focus).

High rigor standard: verifiers compare every quote and number against the actual PMC full text. Verbatim/numerical fabrication = automatic high priority for fixing.

### Rubric (1–5 per dimension, per query)

| Dimension | 1 | 5 |
| --- | --- | --- |
| Factual accuracy | Major errors | Fully correct |
| Citation validity | Cited PMIDs missing/unsupported | All PMIDs exist and support claims |
| Completeness | Key papers/concepts omitted | Covers canonical + recent literature |
| DS-preclinical relevance | Generic / off-target | Specific and actionable for DS rodent work |

Plus a binary Hallucination flag: any fabricated PMID, unsupported claim, or invented model/gene association ⇒ flag = 1.

### High-rigor verification – tiered

Tier 1 (independent re-synthesis, 8 queries): drawn from the structured bank, weighted toward synthesis/recommendation and anti-hallucination probing. Independent verifier runs their own PubMed search, writes an independent answer, then a blinded comparison scores agreement on facts and citations. This captures omissions in addition to potential fabrication.

Tier 2 (citation-only verification, remaining ~17 structured + all wild): verifier confirms each cited PMID exists (PubMed lookup) and that the paper supports the specific claim. Flags unsupported/fabricated citations. Faster; catches hallucination but not omissions.

### Metrics reported

% answers with ≥1 hallucinated citation (overall + per domain)

% citations valid (exist AND support claim)

Mean rubric dimension scores per domain

Tier-1 factual agreement rate (LLM vs independent synthesis)

Deep Dive: suggestion-trigger accuracy (DD-1 to DD-3); mean verbatim-fidelity / numerical-accuracy / source-labeling scores (DD-4 to DD-8); not-stated-discipline and non-OA-refusal pass rates; count of verbatim/numerical fabrications (each = P0)

Bug list prioritized P0 (blocks use) / P1 (degrades) / P2 (polish)

## Timeline (Standard setup – 10 working days, ~30 min/day)

### Week 1

Structured bank execution (30 min/day). Scorers run ~2 assigned Track-A queries/day on the default model, record answers, score rubric, perform Tier-2 citation verification. Daily 10-min async check-in and progress updates via Zulip.

Day 4 – Tier-1 high-rigor standard + Deep Dive suggestion tests (30 min). Independent Verifiers begin PubMed re-synthesis on Tier-1 queries. Scorers run DD-1 to DD-3 (Deep Dive OFF suggestion-trigger tests – quick, ~5 min each) and note which PMIDs are OA-tagged for use in DD-4 to DD-6.

Day 5 – Week-1 sync (30 min). Review aggregate scores so far, triage surfaced bugs, calibrate any rubric drift, confirm Tier-1 comparison + Deep Dive extraction assignments for Week 2.

### Week 2

Day 6 – Deep Dive extraction + Wild track (30 min). Assigned scorers run DD-4 to DD-6 (Deep Dive ON, verbatim extraction against PMC – heaviest queries, ~20 min each, so 1–2 per scorer). Others begin their first wild-track question (Track B) with rubric + Tier-2 verification. Verifier/lead begins blinded Tier-1 comparison scoring.

Day 7 – Deep Dive refusal + Wild track (30 min). Run DD-7 to DD-8 (non-OA refusal + not-stated discipline). Second wild-track question per researcher. Complete Tier-1 comparison scoring; reconcile discrepancies; record agreement metrics. Optional DD-9/DD-10 edge cases if time permits.

Day 8 – Buffer / catch-up (30 min). Finish any outstanding queries, citation checks, or Deep Dive verbatim comparisons; final anti-hallucination probe review.

Day 9 – Consolidation (30 min). Test Lead aggregates all scores (standard + Deep Dive), computes metrics, finalizes prioritized bug list. Developer files/reproduces all confirmed bugs as GitHub issues with steps-to-reproduce.

Day 10 – Report & debrief (30 min). Final consolidated report drafted (metrics + Deep Dive assessment + bug list + beta go/no-go recommendation). Joint debrief: top failure modes, recommended fixes, next-iteration priorities.

## Deliverables & Acceptance Criteria

Consolidated testing report (report_T21RS_LLM_testing.doc): methods, metrics table, per-domain scores, Tier-1 agreement, hallucination rate, Deep Dive assessment (suggestion-trigger accuracy, verbatim-fidelity/numerical-accuracy scores, fabrication count), prioritized bug list, beta-readiness recommendation.

Scored query dataset (T21RS_scored_queries.csv): one row per query with rubric scores, hallucination flag, citation-validity counts, verifier ID, track, and Deep Dive columns.

GitHub issues filed in asathyanesan/ds-research-tool-test for every confirmed bug, labeled P0/P1/P2 with reproduction steps.

Acceptance: all ~25 structured queries scored; all 8 Tier-1 comparisons completed; ≥80% of wild-track queries scored; all 8 Deep Dive queries scored with verbatim verification completed for DD-4 to DD-6; bug list filed; report delivered by end of Day 10.

## Assumptions

Default model is fixed for the test window (no mid-test model/config changes); UD confirms and records the exact model + version used.

The 1,200+ bibliography is static during testing; any mid-test update is logged.

Scorers have PubMed access and basic DS preclinical domain knowledge; undergrads handle only PMID-existence checks.

No compute/HPC resources required – this is human evaluation of a live web tool plus a shared spreadsheet and the repo issue tracker.

30 min/day assumes focused effort; Day 8 is an explicit buffer so a missed day doesn't break the schedule. With the expanded team (~9 active testers), per-person load is ~3–4 queries – comfortable. If anyone drops out, the Test Lead redistributes their queries; the buffer day absorbs shortfalls.

Deep Dive verbatim verification requires PMC Open Access access for the chosen OA papers; verifiers confirm OA status from the tool's own [OA – full text available] tags before running extraction tests.

Deep Dive focus detection relies on numeric PMIDs in the query (regex \b\d{7,9}\b); named-only papers may not trigger focus tagging – DD-9 characterizes this known limitation rather than treating it as a bug.